## Submission Tracker
ENGINEERING DOCUMENTS REGISTER FOR CHHATTISGARH TRANSPORT DEPARTMENT (CTD) AGAINST TENDER NO.: GEM/2025/B/6777914, DATED: 11-10-2025
Sl. No. | Document Description | Transmittal No. | TYPE | Qty. | Category | Milestone |  |  | Document Status | REV-0 |  |  | REV-1 |  | REV-2 |  | REV-3 |  | REV-4 |  | Remarks
[6 empty] | Start Date | End Date | No of Days |  | Planned | Actual | Comment Received | Submitted | Comment Received | Submitted | Comment Received | Submitted | Comment Received | Submitted | Comment Received
1 | 6 Mtr. Cantilever Pole design with 3-5 Meter Arm | 1 | Document |  | Approval | 2026-01-08 | 2026-01-10 | 2 | NA | 2025-12-29 | 2205-12-29 | NA | NA | NA | NA | NA | NA | NA | NA | NA
2 | Staad Report-6 Mtr. Cantilever Pole design with 3-5 Meter Arm | 1 | Document |  | Approval | 2026-01-08 | 2026-01-10 | 2 | NA | 2026-01-08 | 2026-01-08
3 | 7 Mtr. Cantilever Pole design with 3-5 Meter Arm | 1 | Document |  | Approval | 2026-01-08 | 2026-01-10 | 2 | NA | 2026-01-08 | 2026-01-08
4 | Staad Report-7 Mtr. Cantilever Pole design with 3-5 Meter Arm | 1 | Document |  | Approval | 2026-01-08 | 2026-01-10 | 2 | NA | 2026-01-08 | 2026-01-08
5 | 6.3 Mtr. Cantilever Pole design with 6 Meter Arm | 1 | Document |  | Approval | 2026-01-08 | 2026-01-10 | 2 | NA | 2026-01-08 | 2026-01-08
6 | Staad Report-6.3 Mtr. Cantilever Pole design with 6 Meter Arm | 1 | Document |  | Approval | 2026-01-08 | 2026-01-10 | 2 | NA | 2026-01-08 | 2026-01-08
7 | Survey Report - TMC | 2 | Document |  | Approval | 2026-01-10 | 2026-01-12 | 2 | NA | 2026-01-10 | 2026-01-10
8 | 6.3 Mtr. Dual Arm T Pole design with 3 Meter Arm | 3 | Document |  | Approval | 2026-01-12 | 2026-01-14 | 2 | NA | 2025-12-29 | 2205-12-29
9 | Staad Report-6.3 Mtr. Dual Arm T Pole design with 3 Meter Arm | 3 | Document |  | Approval | 2026-01-12 | 2026-01-14 | 2 | NA | 2026-01-12 | 2026-01-12
10 | 6.3 Mtr. Dual Arm T Pole design with 6 Meter Arm | 3 | Document |  | Approval | 2026-01-12 | 2026-01-14 | 2 | NA | 2026-01-12 | 2026-01-12
11 | Staad Report-6.3 Mtr. Dual Arm T Pole design with 6 Meter Arm | 3 | Document |  | Approval | 2026-01-12 | 2026-01-14 | 2 | NA | 2026-01-12 | 2026-01-12
12 | ITMS Outdoor Cabinet (Electrical) Drawing | 4 | Document |  | Approval | 2026-01-13 | 2026-01-15 | 2 | NA | 2026-01-13 | 2026-01-13
13 | ITMS Outdoor Cabinet (Network) Drawing | 4 | Document |  | Approval | 2026-01-13 | 2026-01-15 | 2 | NA | 2026-01-13 | 2026-01-13
14 | Gantry Design for 3M X 1.5M VMD | 5 | Document |  | Approval | 2026-01-20 | 2026-01-22 | 2 | NA | 2026-01-12 | 2026-01-12
15 | Staad Report-Gantry Design for 3M X 1.5M VMD | 5 | Document |  | Approval | 2026-01-20 | 2026-01-22 | 2 | NA | 2026-01-20 | 2026-01-20
16 | Gantry Design for 4M X 2M VMD | 5 | Document |  | Approval | 2026-01-20 | 2026-01-22 | 2 | NA | 2026-01-20 | 2026-01-20
17 | Staad Report-Gantry Design for 4M X 2M VMD | 5 | Document |  | Approval | 2026-01-20 | 2026-01-22 | 2 | NA | 2026-01-20 | 2026-01-20
18 | Gantry Design upto 19 Meter clear Span | 5 | Document |  | Approval | 2026-01-20 | 2026-01-22 | 2 | NA | 2026-01-20 | 2026-01-20
19 | Staad Report-Gantry Design upto 19 Meter clear Span | 5 | Document |  | Approval | 2026-01-20 | 2026-01-22 | 2 | NA | 2026-01-20 | 2026-01-20
20 | FAT-Local Processing Unit (LPU) | 6 | Document |  | Approval | 2026-01-20 | 2026-01-22 | 2 | NA | 2026-01-20 | 2026-01-20 | 2026-01-21
21 | FAT-8 Port Field Switch (8PFS) | 6 | Document |  | Approval | 2026-01-20 | 2026-01-22 | 2 | NA | 2026-01-20 | 2026-01-20 | 2026-01-21
22 | FAT-Radar (RDR) | 6 | Document |  | Approval | 2026-01-20 | 2026-01-22 | 2 | NA | 2026-01-20 | 2026-01-20 | 2026-01-21
23 | FAT-2KVA Field UPS with 120 Minute Backup (FUPS) | 6 | Document |  | Approval | 2026-01-20 | 2026-01-22 | 2 | NA | 2026-01-20 | 2026-01-20 | 2026-01-21
24 | FAT-Speed Display (SPED) | 6 | Document |  | Approval | 2026-01-20 | 2026-01-22 | 2 | NA | 2026-01-20 | 2026-01-20 | 2026-01-21
25 | FAT-PTZ Camera (PTZC) | 6 | Document |  | Approval | 2026-01-20 | 2026-01-22 | 2 | NA | 2026-01-20 | 2026-01-20 | 2026-01-21
26 | FAT-ANPR Camera (ANPR) | 6 | Document |  | Approval | 2026-01-20 | 2026-01-22 | 2 | NA | 2026-01-20 | 2026-01-20 | 2026-01-21
27 | FAT-Junction Box (JB) | 6 | Document |  | Approval | 2026-01-20 | 2026-01-22 | 2 | NA | 2026-01-20 | 2026-01-20 | 2026-01-21
28 | FAT-ITMS Junction Box (ITMSJB) | 6 | Document |  | Approval | 2026-01-20 | 2026-01-22 | 2 | NA | 2026-01-20 | 2026-01-20 | 2026-01-21
29 | FAT-Straight Poles (STPOLE) | 6 | Document |  | Approval | 2026-01-20 | 2026-01-22 | 2 | NA | 2026-01-20 | 2026-01-20 | 2026-01-21
30 | FAT-Cantilever Poles (CTPOLE) | 6 | Document |  | Approval | 2026-01-20 | 2026-01-22 | 2 | NA | 2026-01-20 | 2026-01-20 | 2026-01-21
31 | FAT-Gantry Poles (GTPOLE) | 6 | Document |  | Approval | 2026-01-20 | 2026-01-22 | 2 | NA | 2026-01-20 | 2026-01-20 | 2026-01-21
32 | [7 empty] | 0 | NA
33 | [7 empty] | 0 | NA
34 | [7 empty] | 0 | NA
35 | [7 empty] | 0 | NA
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50