## Synopsis
Sno. | Particulars | Details
1 | Name of Organization | Department of Home Affairs¦¦Punjab Police Housing Corporation
2 | Contact Details Organzation | TEL. NO.4080111, 4080112 & FAX No.4080107
3 | Consultant Name
4 | Consultant Contact Details
5 | Location (State ; City) | SAS Nagar , Punjab
6 | Type of Work (Surveillance/ ITMS/ATCS etc) | City Surveillance
7 | Tender No | 22/2023-24
8 | Tender ID | 2024_DHA_114802_1
9 | Website | www.eproc.punjab.gov.in
10 | Release of RFP | 2024-01-04 17:00
11 | Bid Sale Date | 2024-01-04 17:00
12 | Last date of Submission | 15-Jan-2024 11:00 AM
13 | Prebid Queries submission date | NA
14 | Pre bid Date
15 | Pre-Bid Mode (Online/ Offline)
16 | Pre-bid Venue/link
16 | Scope of Work | Supply, Installation, Testing, Commissioning, Operations and Maintenance of City Surveillance and Traffic Management System with Command and Control Centre in S.A.S Nagar City, Punjab.
17 | Implentation Duration | T + 180 days
18 | Operation and Maintennance Duration | 3 Years
19 | Estimated Cost (Including/Exclusive )GST | Not Found
20 | EMD Value | 22,00,000
21 | EMD Mode of Submission | Online (BG)
22 | Last Date for submission of hard copy of bid along with original EMD and tender fee | Not Found
23 | Tender Fee | 5900
24 | Tender Fee Mode of Submission | Online
25 | Performance Bank Guarantee | 5%
26 | Validity of Bid | 90
27 | Hardcopy submission | Not Found
28 | Consortium Status | Allowed
29 | No of Consortium Allowed (If applicable) | Not Found
30 | Specific Make status | Not Found
31 | Type of BID (QCBS, L1, RA)(Q2/Q3) | L1
32 | RA Clause (if Applicable) | NO
33 | Capex and Opex Ratio | Not Found
34 | Purchase Preference Clause | Not Given
35 | Minimum Qulaifying marks | Not Given
36 | Joint Several Liability | Allowed
37 | Additional performance Security Clause | Not Given
38 | Manpower Penalty | Refer SLA
39 | Delivery Time perid (Penalty if applicable) | Refer SLA
40 | Mobalization Advance Clasue | Not Given
41 | Abnormal / Unbalance bid Clause | Not Given
42 | Qualifying Status of Technosys
43 | Qualifying Status of Sensecure
44 | Qualifying Status of Infobase

## PQ
1.5) QUALIFICATION OF BIDDERS
a) Eligibility Criteria
# | Criteria | Documentary Evidence | Page No.
1 | The bid shall be submitted by an individual company as a Sole Bidder or as a Consortium of 2 companies for this project. b. The Sole Bidder / Lead bidder & Consortium members should be registered under Indian Companies Act, 1956/ 2013/ Sole proprietorship. c. The Sole Bidder or the Lead Bidder, in case of a Consortium, should have completed atleast 5 years of Operations in India, as on bid submission date | Lead bidder / Consortium agreement & undertaking with roles and responsibilities of scope of work in this project ii. Copy of Certification of Incorporation/ Registration Certificate iii. Memorandum of Association and Articles of Association iv. Work order/ Purchase Order/ Contract Agreement to certify that the Bidder has been in Operations for atleast 5 years in India
2 | Average Annual Turnover during the last three financial years (FY 2020-21, 2021-22 & 2022-23) should be minimum INR 10 Crores. i) In case of sole bidder: INR 10 Crores. ii) In case of a Consortium a) Lead Bidder - Min. INR 6 crore b) Consortium member - Min. INR 4 crore. | Audited financial statements for the last three Financial Years i.e. 2020-21, 2021-22 and 2022-23. And j) Certificate from the Statutory Auditor/ Chartered Accountant on turnover details for the last three FYs. Note: In case the financial statements for FY 2022-23 are not audited then Provisional Certified Financial statement for FY 2022-23 by CA can be provided.
3 | The Net Worth of the Sole/ Lead bidder and consortium partner shall be positive for each of the last 3 audited financial years. | Certificate from the Statutory Auditor/ Chartered Accountant on positive net-worth for the last three (3) financial years.
4 | The bidder must have completed/ executed similar nature of works in India/ abroad during the last 10 years as on bid submission date, as mentioned below:- 01 Project of min. 7 Crores, having minimum 300 cameras or 02 Projects, each of min. 5 Crores, having minimum 200 cameras or 03 Projects, each of min. 3.5 Crores, having minimum 150 cameras Similar Project- Supply, Installation, Testing, Commissioning in any City Surveillance project consisting of City-wide video surveillance (with Video analytics/ VMS)/ Intelligent Traffic Management Systems/ ATMS on highways/ ITS on highways with e-Challan system connected with vehicle data bases and Integrated Command and Control Centre. The bidder should also have experience of Operation & Maintenance of the similar project for at least one year. | Work order/ purchase order/ agreement and Satisfactory completion Certificate from the concerned authority, showing nature of work, value and number of cameras installed.
5 | The Bidder should have a valid GST, PAN, ESI & EPF registration with latest updated return filed. | Copy of GST, PAN, ESI & EPF Registration certificate with latest compliances. In case of unavailability of EPF/ESI number, an Undertaking should be submitted with the technical bid that ESI/EPF number will be arranged within one month from the date of allotment of work.
6 | The Sole Bidder or any of Consortium members, should jointly possess any Two (2) of the below certifications, which are valid at the time of bidding: i. – ISO 9001:2015 for Quality Management System ii. – ISO 27001:2013 for Information Security Management System. iii. – ISO 20000:2018 for IT Service Management. | Copies of valid certificates
7 | The Bidder should have direct authorization from the Original Equipment Manufacturer (OEM) for the equipment’s i.e. Cameras, Software, Active Network equipment, Bandwidth service provider, Displays, Servers, Desktop and Storage offered. | Manufacturer’s Authorization Form to be submitted as per the Format terms.
8 | The Sole Bidder and each of Consortium members and its Partner/ Directors, at the time of bid submission, shall not have been blacklisted/ debarred by any Central Government/ State Government/ Semi Government/ Corporation/ PSU or any other Government Institution/ Regional Authority in India. | The Sole Bidder and each of Consortium members shall furnish an undertaking signed by the Authorized signatory of the company to be provided on Non-Judicial Stamp Paper duly attested by notary public.
9 | The Bidder should have an office with project / service team in SAS Nagar/ Chandigarh UT/ Panchkula. Note: In case Bidder does not have a local office at the time of bid submission, Bidder shall furnish an undertaking that an office shall be opened within ten days of issue of Letter of Acceptance. | Notarized copy of ownership document/ Rent agreement. or ii. Undertaking signed by authorized signatory of bidder stating the local office will be established within ten (10) days) days from the issue of LOA date.

## TQ
Not Found

## Manpower Deployment
(2) Manpower a) Project Manager: (01 no.) The Bidder shall be responsible to deploy dedicated Project Manager(s) with minimum 10 years’ experience in similar field including City surveillance, Traffic Management and Command & Control Centre till the completion of the project. The qualification of the project Manager should be qualified B.E./ B.Tech Electronics/ Electrical/ IT/ Computer Science and experience of 10 years in similar field. CV’s for Project Manager (s) shall be provided with the bid and evaluated during presentation scoring b) Field Engineer: (Minimum 4 nos.) B. Tech / Diploma with 3 years’ experience in similar projects as per requirements till the completion of the project and O&M period. c) Any additional manpower, if required will be provided by the SI at his own cost.

## Timeline,Milestones and Payment
1.15) PAYMENT SCHEDULE
S.NO | PAYMENT TERMS | PAYMENT
1 | Delivery and Inspection of Hardware/ Equipment at Site/ PPHC Stores | Up-to 60% of Project value (CAPEX) on prorata basis.
2 | Installation, testing & commissioning | Up-to 10% of Project value (CAPEX) on prorata basis.
3 | Final acceptance test by the deptt. and Go Live of the Project as per the definition mentioned in RFP. | Up-to 20% of Project value (CAPEX) on prorata basis.
4 | Free AMC/ Warranty Period: | i) 10% of CAPEX will be paid in 4 Quarterly Installments on prorata basis after the end of each quarter, during free AMC period, after verification of SLA’s as per the satisfaction of PPHC. ii) Payment against MPLS connectivity will be released at the end of each quarter.
5 | Additional comprehensive AMC Period: | Payment of OPEX and MPLS connectivity will be released on monthly basis, on production of bill and EPF and ESI payment receipt.
1.16) PROJECT TIMELINES
Sr. No | Milestone | Deliverables | Timeline
1 | Date of Agreement signing | (within 15 days from LoA along with submission of Performance Bank Guarantee) | T
2 | Project Planning | Detailed Project Plan ii. Survey and Detailed Design of all the solutions components iii. Design Approvals iv. Required Infrastructure Plan & Approval | T + 10 days
3 | Delivery Of BOM | All the BOM mentioned hardware and softwares shall be procured and delivered Stock entry of Hardware and Verification of Hardware by PPHC/Representative of PPHC | T + 90 days
4 | Installation, Commissioning of Hardware | Weekly and Monthly Progress Reports ii. Hardware Installation and configuration iii. Necessary Software Configuration iv. Testing-Performance, Scalability, Systems Integration, Security Testing, Systems Acceptance Test, etc. v. Develop Training Materials | T + 150 days
5 | Testing & Go-Live | Final Acceptance Testing Training & Change management ii. User Training iii. Operational System Acceptance iv. Go-Live of Project | T + 165 days
|  | Go Live Certification (T1) | T + 180 days
7 | Operation & Comprehensive Maintenance:- System Integrator (SI) has to follow the SLA’s defined during the maintenance phase. System Integrator (SI) will be solely responsible for the deliverables. SLA Compliance Reports, Audits |  | T1+36 months from the date of Go-Live of whole project
NOTE:-  T is the date of signing of contract with the System Integrator (SI).  T1 is the date of Go-Live of the contract.

## SLA
1.48) SERVICE LEVEL STANDARDS & AGREEMENT:
Service Level Agreement (SLA) is to be signed between PPHC and the selected Bidder for the project. SLA defines the responsibility of the vendor in ensuring the project performance based on the agreed Indicators as detailed in the Agreement. This section defines various Service Level Indicators for the Project. Sufficient design considerations and requisite spare & manpower availability should be ensured to achieve the uptime standards. PPHC would monitor the compliance of SLA achievements at regulated intervals and release payment for Operations & Maintenance accordingly. The table below summarizes the indicative Performance Indicators for the services to be offered by the selected bidder. The equipment and services availability should be recorded electronically (through NMS including uptime %) and physically by the SI.
S. No. | SLA Parameter | SLA Target
1 | Availability of each component in each quarter of year–  Surveillance Cameras  Traffic Management Cameras/ devices in field  Outdoor UPS Power  Outdoor Switches and all field equipment. | 97%
2 | Availability of each component in each quarter of year  Control Room Switches and other Active/ Passive components  NMS, VMS, ITMS  Video Wall  Network connectivity | 99.5%
3 | Availability of “Data Centre & Command and Control Centre (CCC) equipment, Storage and software | 99.5%
4 | Availability of O&M Personnel for call logging, troubleshooting, & rectification | 99%
1.49) SEVERITY LEVEL DEFINITION

## LIQUIDATED DAMAGES & PENALTIES
1.41) LIQUIDATED DAMAGES
i. The Contractor shall ensure due diligence to achieve progress of work as per the milestones in the DNIT.
ii. In case of delay, the Contractor shall, notwithstanding issuance of a prior notice in this regard, pay prospectively as liquidated damages that PPHC may levy, for every week of the period for which the work remains un-commenced after 10 days of the issue of acceptance letter; or the minimum progress of work stated above is not achieved; or the work remains unfinished after the completion date.
iii. In case of continued default or shortfall in progress, PPHC may go on enhancing the levy of liquidated damages, each time limited to 1% of the amount of contract per week of further default subject to maximum limit of 10% the Contract value.
iv. The Chief Engineer, PPHC on representation from Contractor, may reduce the amount of liquidated damages after passing speaking orders and his decision in writing shall be final and binding.
v. If the Intended Completion Date is extended after liquidated damages have been paid, PPHC shall correct any overpayment of liquidated damages by the Contractor by adjusting the next payment certificate.
1.52) PENALTIES:
The successful Bidder shall be penalized on service disruption beyond permissible limits as mentioned in the Service level agreement. The upper limit of penalty would be capped at 10% of the OPEX value for each quarter. In case the calculated penalty crosses 10% penalty of the OPEX value in 2 subsequent quarters, GSCDCL reserves the right to unconditionally invoke the termination clause.
Description | Availability | Penalty Value
Availability of each component in each quarter of year:–  Surveillance Cameras  Traffic Management Cameras/ devices in field  Outdoor UPS Power  Outdoor Switches and all field equipment | Within SLA | Nil
| Between 96% to <97% | 0.1% on the OPEX payable for respective quarter
| For Every 0.5% drop from <96% | Additional 0.2% on the OPEX payable for respective quarter
Availability of each component in each quarter of year:- | Within SLA | Nil
| Between 98.5% to <99.5% | 0.1% on the OPEX payable
Control Room Switches and other Active/ Passive components NMS, VMS, ITMS Video Wall Network connectivity | For Every 0.5% drop from <98.5% | Additional 0.2% on the OPEX payable for respective quarter
Availability of “Data Centre & Command and Control Centre (CCC) equipment Storage and software | Within SLA | Nil
| Between 98.5% to <99.5% | 0.1% on the OPEX payable for respective quarter
| For Every 0.5% drop from <98.5% | Additional 0.2% on the OPEX payable for respective quarter
Availability of personnel for logging calls and problem rectification | For <= 1% of the calls not getting responded in less than or equal to 30 minutes per quarter | Nil
| For > 1% of the calls not getting responded in less than or equal to 30 minutes per quarter | 0.1% of the OPEX payable for respective quarter
Availability of Project Manager and Field Engineers having experience as mentioned in the Technical Bid of the agency | Within SLA | Nil
| Absence of for 01 day (upto 07 days) | Rs. 3000/- per day (For Project Manager) Rs. 1000/- per day, per person (For Field Engineer)
| Absence for more than 07 days (upto 14 days | Rs. 5000/- per day (For Project Manager) Rs. 2000/- per day, per person (For Field Engineer)
| Absence for more than 14 days in a month | No payment for the month
Note: Penalties on account of service disruption in Network connectivity beyond permissible limits will be deducted from the payment of Bandwidth network provider.

## BOQ
Item Rate BoQ
Tender Inviting Authority: Managing Director, Punjab Police Housing Corporation
Name of Work: Supply, Installation, Testing, Commissioning, Operations & Maintenance of City Surveillance & Traffic Management System with Integrated Command & Control Centre in S.A.S. Nagar, Punjab
Contract No: 22/2023-24
Name of the Bidder/ Bidding Firm/ Company :
PRICE SCHEDULE (This BOQ template must not be modified/replaced by the bidder and the same should be uploaded after filling the relevent columns, else the bidder is liable to be rejected for this tender. Bidders are allowed to enter the Bidder Name and Values only )
NUMBER # | TEXT # | NUMBER # | NUMBER # | TEXT #
Sl. No. | Name of Goods or Related Service | Rate INCLUDING ALL TAXES in INR Rs. P | Total Amount including all taxes Rs. P | TOTAL AMOUNT In Words
1 | 2 | 13 | 53 | 55
1 | Total CAPEX price (from table 5.2 of Section V) including free comprehensive warranty for 3 years |  | 0 | INR Zero Only
2 | Total price for MPLS connectivity (from table at 5.3 of Section V) |  | 0 | INR Zero Only
Total in Figures |  |  | 0 | INR Zero Only
Quoted Rate in Words |  | INR Zero Only
Validate
Print
Help

## LOCATIONS
Not Found

## Query Format
Not Found